## Slide 1: State Incident Response Support to Locals “We don’t stop an election; we figure out how to proceed.”
NASED Winter Conference ● February 2, 2025

## Slide 2: The Makeup of A Response
Build
Respond
Evaluate

## Slide 3: The Makeup of A Response
BUILD
Respond
Evaluate
Monthly partner meetings
Tabletop the Vote
Statewide Exercise w/Emergency Management
Conferences
Emergency Response HUB and New Director Training Module
Huddles
Stationed at EOC for elections
Security Briefings
Field Specialists
ARKs (Attack Response Kits)

## Slide 4: The Makeup of A Response
Build
Respond
EVALUATE
Post-exercise hot washes & after actions
Post-election lessons learned
Return to “Build” steps

## Slide 5: Response Mode
Build
RESPOND
Evaluate
Absentee by mail delayed (UOCAVA 9/20; CIV 9/24)
Wed./Th., 9/25-27: NCSL in Asheville
Friday, 9/27: Helene strikes
  19 days until Early Voting starts
  39 days until Election Day
Saturday, 9/28: Communication and coordination efforts start
  Pipe bursts at NCSBE (unrelated)

## Slide 6: Response Mode
Build
RESPOND
Evaluate
Monday, 9/30:
  8 AM: 14 county election offices unable to open
  9 AM: Post-storm Assessment & Response Meetings start
  2 PM: NCEM Briefing
  4 PM: Emergency State Board Meeting held (Resolution #1)

## Slide 7: Response Mode
Build
RESPOND
Evaluate
Tuesday, 10/1:
  9 AM: Post-storm Assessment & Response Meetings
  10:30 AM: Press Conference
Wednesday, 10/2:
  9 AM: Post-storm Assessment & Response Meetings
  11 AM: Meet w/Senator Tillis’ staff
  2:30 PM: Meet w/legislative staff

## Slide 8: Response Mode
Build
RESPOND
Evaluate
Thursday, 10/3:
  9 AM: Post-storm Assessment & Response Meetings
  1 PM: NCEM Touchpoint
  2:30 PM: Resolution #2 work session
  3:30 PM: USPS coordination meeting
  5:30 PM: CISA meeting

## Slide 9: Response Mode
Build
RESPOND
Evaluate
Friday, 10/4:
  9 AM: Post-storm Assessment & Response Meetings
  10:30 AM: Resolution #2 work session
  11:30 AM: Call with board member in affected county
  1:30 PM, 4:30 PM, and Saturday: Review Resolution #2 with board members

## Slide 10: Response Mode
Build
RESPOND
Evaluate
Monday, 10/7:
  8 AM: Call with ES&S
    All offices are open
  9 AM: Post-storm Assessment & Response Meetings
  10 AM: Monday Morning Kickoff
  11 AM: State Board Meeting Emergency Resolution
  1:15 PM: Availability to affected counties
  2 PM: Press Conference
  3 PM: CBS News
  4 PM: NCEM Touchpoint

## Slide 11: Response Mode

## Slide 12: Response Mode

## Slide 13: Response Mode
Attack Response Kits (ARKs)
“Out Past Curfew” Letters
Authorization for gas
Old-school communication methods & outreach
Paper backups and manual methods
Over communicate
  Injured player on the field
  Report outs to reduce meetings
Personal situations to address

## Slide 14: Response Mode
Press conferences
Media interviews (focus on local)
Print ads
Social media
Flyers
Dedicated webpage
Display banners
Sandwich boards

## Slide 15: Early voting opened in ALL North Carolina counties on October 17, 2024 – 19 days after Hurricane Helene moved through WNC   76 of 80 planned early voting sites in disaster declared counties with power     Legislation required 4 additional sites in final week (Henderson, McDowell)
Delivering Voting Through Helene & High Water

## Slide 16: Delivering Voting Through Helene & High Water
Affected counties outpaced EV turnout
  2% points higher
300 affected voters delivered ABM ballot out of county (special Helene provision)

## Slide 17: Delivering Voting Through Helene & High Water
Vast majority of Election Day sites were open
7 “blank slate tents” used: Yancey (4), Buncombe (1), Burke (1), Haywood (1)

## Slide 18: Delivering Voting Through Helene & High Water

## Slide 19: So how does the State Elections Office support the locals through major incidents?
No formula or perfect answer
Push the “insurance policy”
All hazards approach
Communicate, huddle, & execute the play
Make the asks
Use the bigger microphone
Be human not just business

## Slide 20: Questions and Contact Information
Karen Brinson Bell, Executive Director
North Carolina State Board of Elections
karen.bell@ncsbe.gov